## Slide 1
A Holistic Approach to Transformation Planning, Stakeholder Engagement, Training, and Adoption
Comprehensive Change Management Strategy

## Slide 2
Table of Contents
04
05
06
07
08
09
Change Management Plan
The Need for Change & Vision
Change Management Framework (ADKAR + Ko…
Stakeholder Impact Analysis
Communication & Engagement Strategy
Training & Capability Building Plan

## Slide 3
Table of Contents
10
11
12
13
Resistance Management & Risk Matrix
Adoption Roadmap (Phased Rollout)
Adoption Milestones & Success Metrics
Executive Close: What We Deliver

## Slide 4
Change Management Plan
Scope: business restructuring, software rollout, or operational pivot
Scope of Transformation
Plan effective date: [Date]
Plan Implementation Date
Change owner: [Transformation Director/PMO Role]
Change Ownership
Lead sponsor: [Lead Sponsor Name & Title]
Lead Sponsor Information
Transformation name: [Project/Transformation Name]
Transformation Details
Comprehensive Change Management Strategy
4

## Slide 5
The Need for Change & Vision
Vision statement
a unified way of working that enables teams to deliver reliably at scale
What success looks like
adoption, proficiency, and sustained performance behavior
Desired future outcomes
faster throughput, clearer ownership, and measurable service improvements
Operating pain points
cost leakage, service delays, and cross-team handoff breakdowns
Current-state friction
manual workflows, inconsistent execution, and slow decision cycles
Comprehensive Change Management Strategy
5

## Slide 6
Change Management Framework (ADKAR + Kotter)
Reinforcement using metrics, recognition, and continuous improvement loops
Ability supported by practice, coaching, and early-life support
Knowledge via role-based training, job aids, and process clarity
Desire through compelling outcomes, benefits, and leadership commitment
Awareness of the need, and why the change matters now
ADKAR: Awareness
ADKAR: Desire
ADKAR: Knowledge
ADKAR: Ability
ADKAR: Reinforcement
Comprehensive Change Management Strategy
6

## Slide 7
Stakeholder Impact Analysis
Create Targeted Support Plan
Create a targeted support plan by segment to avoid one-size-fits-all delivery
Identify Key Stakeholders
Identify change champions and critical decision-makers for each impacted area
Define Required Support
Define required support: information only, training, hands-on enablement, or close coaching
Assess Change Severity
Assess change severity using impact level and likelihood of workflow disruption
Map Impacted Teams and Roles
Map impacted teams and roles across processes, systems, governance, and customer touchpoints
Comprehensive Change Management Strategy
7

## Slide 8
executive briefings, town halls, team huddles, and targeted role emails
Communication channels
Communication & Engagement Strategy
business rationale, benefits, what changes for each role, and how to get help
Key messages
weekly operational updates plus monthly leadership checkpoints
Cadence
Q&A sessions, listening posts, and structured feedback loops
Engagement mechanisms
rapid routing for blockers, misconceptions, and urgent operational risks
Escalation path
Comprehensive Change Management Strategy
8

## Slide 9
Training & Capability Building Plan
Pre-go-live assessments and post-training proficiency validation
Super-user network, helpdesk playbooks, and escalation SLAs
Quick-start guides, SOP updates, and system job aids
Onboarding sessions, hands-on labs, scenario walkthroughs, and office hours
Define competencies per job family and map to training modules
Role-based learning design
Delivery roadmap
Documentation set
Support resources
Readiness checkpoints
Comprehensive Change Management Strategy
9

## Slide 10
Friction Point | Mitigation Tactic | Owner
Unclear process ownership | Publish RACI, run role walk-throughs, and confirm handoffs in working sessions | Transformation Lead
Tool adoption anxiety | Provide guided labs, super-user coverage, and a rapid help escalation lane | Enablement Manager
Change fatigue | Simplify rollout scope, batch communications, and protect time for training practice | Program Director
Resistance Management & Risk Matrix
Comprehensive Change Management Strategy
10

## Slide 11
hypercare wrap-up
process refinement
Phase 4: Stabilize
controlled cutover with monitoring
issue triage
Phase 3: Go-live
role training
pilot usage
Phase 2: Enablement
stakeholder alignment
training development
Phase 1: Readiness build
Adoption Roadmap (Phased Rollout)
Comprehensive Change Management Strategy
11

## Slide 12
readiness sign-off
go-live readiness
stabilization completion
Milestone targets
feedback sentiment
ticket resolution time
repeat issue rate
Experience KPI set
assessment scores
task success rate
time-to-complete reduction
Proficiency KPI set
% trained
% active users
% process compliance
Adoption KPI set
Adoption Milestones & Success Metrics
Comprehensive Change Management Strategy
12

## Slide 13
Executive Close: What We Deliver
Resistance mitigation and risk ownership that protect adoption during rollout and stabilization
Resistance Mitigation and Risk Ownership
Clear communication and training pathways with measurable readiness and proficiency outcomes
Clear Communication and Training
Targeted stakeholder support that reduces disruption and accelerates confident usage
Targeted Stakeholder Support
A repeatable change management plan that drives awareness, desire, knowledge, ability, and reinforcement
Repeatable Change Management Plan
Comprehensive Change Management Strategy
13